## Summary
Kita Kids Database – Development Plan
Web application for kindergarten staff · Python + TypeScript · local-network server · one developer
Project start | 2026-10-21
Release 1 (core app) live by | 2027-09-21
Release 2 (extras + AI) live by | 2028-02-01
Total duration (weeks) | 67
Number of stages | 17
Number of backlog tasks | 102
Effort Release 1 (days) | 179
Effort Release 2 (days) | 74
Total effort (person-days) | 253
Tasks done | 0
Progress (tasks) | 0%
High-rated risks | 9
Sheets in this workbook
Stages | 17 stages in two releases; effort from the backlog; start date, buffer and availability are inputs
Backlog | All tasks with stage, release, technology, owner, effort, priority, status (filterable)
Requirements | Your 17 features plus 18 suggested ones, mapped to stages and releases
Server Setup | Step-by-step checklist for the Kita server
Tech Stack | Proposed technologies with reasons
Risks | Risk register with score and mitigation
Release 1 is the usable core (login, profiles with safety data, groups, board, calendar, attendance, feedback). Release 2 adds parent communication, daily reports, staff tools and AI.
Estimates are initial assumptions; refine after S0 and S1. Change the availability in Stages!B5 if you work on this part-time.

## Stages
Kita Kids Database – Development Stages
Blue cells are inputs. Effort comes from the Backlog; duration and dates recalculate automatically.
Project start date | 2026-10-21 | Start today (Wed 21.10.2026), as requested
Buffer for meetings, bugs, rework | 20% | Assumption: 20% on top of task effort
Your availability (days per week) | 5 | Assumption: full time. Set e.g. 2.5 if you work on this part-time; all dates move
Public holidays, Kita closing days and your own leave are not included.
Stage ID | Stage | Release | Description | Effort (days) | Duration (weeks) | Start | End | Key deliverable | Status
S0 | Discovery & Requirements | Release 1 | Clarify scope, users, legal basis (Swiss nDSG / German DSGVO), existing hardware | 10 | 3 | 2026-10-21 | 2026-11-10 | Signed-off requirements & data-protection concept | Not started
S1 | UX / HMI Design | Release 1 | Wireframes and clickable prototype for non-technical staff; tablet-friendly; German/English | 14 | 4 | 2026-11-11 | 2026-12-08 | Approved prototype & style guide | Not started
S2 | Architecture & Dev Setup | Release 1 | Tech stack, repo, CI, DB schema, development environment on your own machine | 12 | 3 | 2026-12-09 | 2026-12-29 | Running skeleton (backend + frontend + DB) | Not started
S3 | Server & Infrastructure Setup | Release 1 | Install and secure the Kita server, HTTPS, backups, monitoring (see sheet Server Setup) | 11 | 3 | 2026-12-30 | 2027-01-19 | Staging server running with tested backup/restore | Not started
S4 | Authentication & Access Control | Release 1 | Login, roles (Admin / Teacher / Guest), user-admin page | 20 | 5 | 2027-01-20 | 2027-02-23 | Secure login with role-based access | Not started
S5 | Kids Profiles, Safety & Archive | Release 1 | Profiles, parents, emergency contacts, pick-up persons, allergy alerts, consents, photos, archive | 29 | 7 | 2027-02-24 | 2027-04-13 | Kids profile module | Not started
S6 | Groups & Task Board | Release 1 | Group selection, group views, agile board with backlog | 15 | 4 | 2027-04-14 | 2027-05-11 | Group module with Kanban board | Not started
S7 | Calendar & Events | Release 1 | Holidays, events, birthdays, group and Kita-wide views | 10 | 3 | 2027-05-12 | 2027-06-01 | Calendar module | Not started
S8 | Attendance, Incidents & Emergency | Release 1 | Daily attendance, absences, incident log, printable emergency list, today dashboard | 13 | 4 | 2027-06-02 | 2027-06-29 | Daily-operations module | Not started
S9 | Feedback & Crash Reporting | Release 1 | Problem / idea / change-request form, automatic crash reports to developer | 8 | 2 | 2027-06-30 | 2027-07-13 | Feedback module | Not started
S10 | Data Separation & Security Hardening | Release 1 | Current vs. archived data, encryption, audit log, parent data export, security review | 12 | 3 | 2027-07-14 | 2027-08-03 | Security checklist passed | Not started
S11 | Testing & Pilot | Release 1 | Automated and manual tests, user acceptance test with Kita staff, bug fixing | 18 | 5 | 2027-08-04 | 2027-09-07 | UAT sign-off | Not started
S12 | Deployment, Training & Go-live | Release 1 | Production release on the Kita server, manual, staff training, support process | 7 | 2 | 2027-09-08 | 2027-09-21 | Release 1 live | Not started
S13 | Parent Communication & Documents | Release 2 | Parent role/portal, announcements, messages, read receipts, document templates | 16 | 4 | 2027-09-22 | 2027-10-19 | Parent communication module | Not started
S14 | Daily Reports, Development & Staff Ops | Release 2 | Daily report, development observations, staff roster, meal plan, waiting list | 20 | 5 | 2027-10-20 | 2027-11-23 | Operations module | Not started
S15 | AI Features | Release 2 | Local AI: search, drafting, translation, suggestions, help assistant | 24 | 6 | 2027-11-24 | 2028-01-04 | AI assistant module | Not started
S16 | Release 2 Testing & Rollout | Release 2 | Tests, user acceptance, bug fixing, deployment and training for new modules | 14 | 4 | 2028-01-05 | 2028-02-01 | Release 2 live | Not started
| Total |  |  | 253 | 67 | 2026-10-21 | 2028-02-01
Stages run one after another because you are the only developer. Light-blue rows are Release 2.
Formulas:
Start = WORKDAY([End, row above],1)
End = WORKDAY([Start],[Duration (weeks)]*5-1)
End = [End, row above]

## Backlog
Task Backlog
Effort (days) is an estimate for one developer; change the blue cells and the Stages sheet recalculates. Filter by stage, release, priority or status.
ID | Stage | Stage name | Release | Task | Feature area | Technology | Owner role | Effort (days) | Priority | Status
T001 | S0 | Discovery & Requirements | Release 1 | Interview Kita management and teachers; collect real workflows | All | Workshops | Product owner | 3 | High | To do
T002 | S0 | Discovery & Requirements | Release 1 | Define user roles and permission matrix (Admin / Teacher / Guest; Parent later) | Access rights | Document | Product owner | 1 | High | To do
T003 | S0 | Discovery & Requirements | Release 1 | Data-protection assessment for children's, parents' and health data (nDSG/DSGVO), photo consent | Security | Document | Product owner | 3 | High | To do
T004 | S0 | Discovery & Requirements | Release 1 | Confirm country/canton and legal basis; name a data-protection contact at the Kita | Security | Document | Product owner | 1 | High | To do
T005 | S0 | Discovery & Requirements | Release 1 | Inventory existing hardware, network, number of PCs/tablets | Server | Checklist | Developer | 1 | High | To do
T006 | S0 | Discovery & Requirements | Release 1 | Define Release 1 / Release 2 scope (MoSCoW) and confirm with Kita management | All | Document | Product owner | 1 | High | To do
T007 | S1 | UX / HMI Design | Release 1 | User personas and task flows for basic-skill users | UX/HMI | Figma / paper | UX designer | 2 | High | To do
T008 | S1 | UX / HMI Design | Release 1 | Wireframes: landing, group view, kids profile, allergy alerts, attendance, board, calendar, admin page | UX/HMI | Figma | UX designer | 5 | High | To do
T009 | S1 | UX / HMI Design | Release 1 | Style guide: large buttons, high contrast, icons + text, group icons (Monkey, Butterflies…) | UX/HMI | Figma | UX designer | 2 | Medium | To do
T010 | S1 | UX / HMI Design | Release 1 | Tablet-first layout guidelines (touch targets, PWA behaviour) | UX/HMI | Figma | UX designer | 1 | High | To do
T011 | S1 | UX / HMI Design | Release 1 | Clickable prototype and usability test with 3–5 Kita staff | UX/HMI | Figma | UX designer | 3 | High | To do
T012 | S1 | UX / HMI Design | Release 1 | German/English UI texts (i18n keys) | UX/HMI | JSON | UX designer | 1 | Medium | To do
T013 | S2 | Architecture & Dev Setup | Release 1 | Choose stack (FastAPI + PostgreSQL + React/TypeScript) and record decision | Architecture | Python, TypeScript | Developer | 1 | High | To do
T014 | S2 | Architecture & Dev Setup | Release 1 | Set up development environment on your computer (Python, Node, Docker, Postgres container) | Architecture | Docker | Developer | 1 | High | To do
T015 | S2 | Architecture & Dev Setup | Release 1 | Create repo, branching, linting, pre-commit, CI pipeline | Architecture | Git, GitHub Actions / Azure DevOps | Developer | 2 | High | To do
T016 | S2 | Architecture & Dev Setup | Release 1 | Design database schema (users, kids, parents, groups, tasks, events, attendance, audit log) | Database | PostgreSQL, SQLAlchemy, Alembic | Developer | 3 | High | To do
T017 | S2 | Architecture & Dev Setup | Release 1 | Backend skeleton with health endpoint, config, logging | Architecture | FastAPI | Developer | 2 | High | To do
T018 | S2 | Architecture & Dev Setup | Release 1 | Frontend skeleton with routing, layout, i18n, API client, PWA manifest | Architecture | React, TypeScript, Vite | Developer | 2 | High | To do
T019 | S2 | Architecture & Dev Setup | Release 1 | Docker Compose files for dev and production | Architecture | Docker Compose | Developer | 1 | Medium | To do
T020 | S3 | Server & Infrastructure Setup | Release 1 | Select and obtain hardware: mini PC or NAS, UPS, second drive for backups | Server | Hardware | Developer | 1 | High | To do
T021 | S3 | Server & Infrastructure Setup | Release 1 | Install Ubuntu Server LTS with disk encryption (LUKS); SSH keys, no password login | Server | Ubuntu, LUKS | Developer | 1 | High | To do
T022 | S3 | Server & Infrastructure Setup | Release 1 | Network: fixed IP (router reservation), local DNS name (e.g. kita.lan), firewall | Server | ufw, router | Developer | 1 | High | To do
T023 | S3 | Server & Infrastructure Setup | Release 1 | Install Docker/Compose and deploy staging stack (PostgreSQL, API, web, Caddy) | Server | Docker Compose, Caddy | Developer | 2 | High | To do
T024 | S3 | Server & Infrastructure Setup | Release 1 | HTTPS with local certificate authority; install root certificate on Kita PCs/tablets | Server | Caddy internal CA | Developer | 1 | High | To do
T025 | S3 | Server & Infrastructure Setup | Release 1 | Mount shared network drive for photos/documents (database stays on the server disk) | Storage | SMB/NFS | Developer | 1 | Medium | To do
T026 | S3 | Server & Infrastructure Setup | Release 1 | Backups: nightly pg_dump + photo sync to second drive; weekly encrypted off-site copy; restore test | Storage | pg_dump, restic, cron | Developer | 2 | High | To do
T027 | S3 | Server & Infrastructure Setup | Release 1 | Automatic security updates, UPS safe shutdown, disk/uptime alerts by email | Server | unattended-upgrades, NUT | Developer | 1 | Medium | To do
T028 | S3 | Server & Infrastructure Setup | Release 1 | Admin runbook: restart, update, restore, add user | Server | Document | Developer | 1 | Medium | To do
T029 | S4 | Authentication & Access Control | Release 1 | Landing page with Login, Admin, Teacher, Guest entry points | Landing page | React | Developer | 2 | High | To do
T030 | S4 | Authentication & Access Control | Release 1 | Login with email/password (Gmail/GMX addresses as account ID), argon2 hashing, sessions/JWT | Login | FastAPI, argon2, JWT | Developer | 4 | High | To do
T031 | S4 | Authentication & Access Control | Release 1 | Email verification and password reset | Login | SMTP, FastAPI | Developer | 2 | Medium | To do
T032 | S4 | Authentication & Access Control | Release 1 | Optional: Google OAuth login (needs internet-reachable redirect; GMX stays email+password) | Login | Authlib | Developer | 3 | Low | To do
T033 | S4 | Authentication & Access Control | Release 1 | Role-based access control (Admin, Teacher, Guest read-only) | Access rights | FastAPI dependencies | Developer | 3 | High | To do
T034 | S4 | Authentication & Access Control | Release 1 | Admin page: all users with access rights; change role; deactivate (admin only) | Access rights page | React, FastAPI | Developer | 3 | High | To do
T035 | S4 | Authentication & Access Control | Release 1 | Guest access: limited read-only view without personal data | Guest | React, FastAPI | Developer | 2 | Medium | To do
T036 | S4 | Authentication & Access Control | Release 1 | Login rate limiting, account lockout, session timeout | Security | FastAPI | Developer | 1 | High | To do
T037 | S5 | Kids Profiles, Safety & Archive | Release 1 | Kids CRUD API with admin-only write permissions | Kids profile | FastAPI | Developer | 3 | High | To do
T038 | S5 | Kids Profiles, Safety & Archive | Release 1 | Profile form: photo, name, gender, language, food preferences, interests | Kids profile | React, TypeScript | Developer | 4 | High | To do
T039 | S5 | Kids Profiles, Safety & Archive | Release 1 | Parents data: name, address, contact; link to children and siblings | Parents | React, FastAPI | Developer | 3 | High | To do
T040 | S5 | Kids Profiles, Safety & Archive | Release 1 | Emergency contacts and authorised pick-up persons (with photo) | Safety | React, FastAPI | Developer | 3 | High | To do
T041 | S5 | Kids Profiles, Safety & Archive | Release 1 | Allergy and medical alerts: banner on profile and group view, admin edit, teacher read | Safety | React, FastAPI | Developer | 3 | High | To do
T042 | S5 | Kids Profiles, Safety & Archive | Release 1 | Consent management: photo, excursion, data-protection consent with dates | Consent | React, FastAPI | Developer | 3 | High | To do
T043 | S5 | Kids Profiles, Safety & Archive | Release 1 | Photo upload, thumbnails, gallery per child; hide photos without consent | Photos | Pillow, file storage | Developer | 4 | Medium | To do
T044 | S5 | Kids Profiles, Safety & Archive | Release 1 | Soft delete and archive with retention period (e.g. 12 months), then purge job | Archive | SQL, APScheduler | Developer | 3 | High | To do
T045 | S5 | Kids Profiles, Safety & Archive | Release 1 | Search, filter and list view of kids | Kids profile | React | Developer | 2 | Medium | To do
T046 | S5 | Kids Profiles, Safety & Archive | Release 1 | Restore from archive (admin) | Archive | FastAPI | Developer | 1 | Medium | To do
T047 | S6 | Groups & Task Board | Release 1 | Group model and admin management of groups (Monkey, Butterflies, Insects…) | Groups | FastAPI | Developer | 2 | High | To do
T048 | S6 | Groups & Task Board | Release 1 | Group drop-down on landing page and group dashboard | Groups | React | Developer | 3 | High | To do
T049 | S6 | Groups & Task Board | Release 1 | Assign kids and teachers to groups | Groups | React, FastAPI | Developer | 2 | High | To do
T050 | S6 | Groups & Task Board | Release 1 | Agile board per group: To do / Doing / Done with drag and drop | Task board | React, dnd-kit | Developer | 5 | High | To do
T051 | S6 | Groups & Task Board | Release 1 | Backlog with prioritisation, assignee, due date, labels | Task board | React, FastAPI | Developer | 3 | High | To do
T052 | S7 | Calendar & Events | Release 1 | Calendar view (month/week/agenda) per group and Kita-wide | Calendar | React, FullCalendar | Developer | 3 | High | To do
T053 | S7 | Calendar & Events | Release 1 | Import holidays (school and public holidays for your region) | Calendar | Python, iCal | Developer | 2 | Medium | To do
T054 | S7 | Calendar & Events | Release 1 | Create/edit events, recurrence, reminders | Calendar | FastAPI | Developer | 3 | High | To do
T055 | S7 | Calendar & Events | Release 1 | Birthday reminders generated from kids profiles | Calendar | FastAPI | Developer | 1 | Medium | To do
T056 | S7 | Calendar & Events | Release 1 | iCal export / subscription (optional) | Calendar | iCal | Developer | 1 | Low | To do
T057 | S8 | Attendance, Incidents & Emergency | Release 1 | Daily attendance: check-in / check-out per group, tablet-friendly | Attendance | React, FastAPI | Developer | 4 | High | To do
T058 | S8 | Attendance, Incidents & Emergency | Release 1 | Absence notes (sick, holiday) entered by staff | Attendance | React, FastAPI | Developer | 2 | High | To do
T059 | S8 | Attendance, Incidents & Emergency | Release 1 | Accident and incident log: date, child, what happened, who was informed | Incidents | React, FastAPI | Developer | 3 | High | To do
T060 | S8 | Attendance, Incidents & Emergency | Release 1 | Printable emergency / evacuation list (PDF) with contacts and allergies | Safety | WeasyPrint | Developer | 2 | High | To do
T061 | S8 | Attendance, Incidents & Emergency | Release 1 | 'Today' dashboard per group: present kids, allergies, absences, birthdays | Groups | React | Developer | 2 | Medium | To do
T062 | S9 | Feedback & Crash Reporting | Release 1 | Feedback button on every page: problem / change request / idea | Feedback | React | Developer | 2 | High | To do
T063 | S9 | Feedback & Crash Reporting | Release 1 | Store feedback and forward to developer (email / Azure DevOps work item) | Feedback | FastAPI, Azure DevOps API | Developer | 3 | High | To do
T064 | S9 | Feedback & Crash Reporting | Release 1 | Automatic crash reporting (frontend + backend) with anonymised context | Feedback | Sentry self-hosted or custom handler | Developer | 3 | High | To do
T065 | S10 | Data Separation & Security Hardening | Release 1 | Separate current and archived data: separate schema/views, clear archive section in UI | Data separation | PostgreSQL schemas | Developer | 3 | High | To do
T066 | S10 | Data Separation & Security Hardening | Release 1 | Encryption in transit (HTTPS) check and field-level encryption for addresses and health data | Security | TLS, pgcrypto | Developer | 3 | High | To do
T067 | S10 | Data Separation & Security Hardening | Release 1 | Audit log: who viewed or changed what | Security | SQL | Developer | 2 | High | To do
T068 | S10 | Data Separation & Security Hardening | Release 1 | Parent data export and deletion tool (data-protection requests) | Security | FastAPI | Developer | 2 | High | To do
T069 | S10 | Data Separation & Security Hardening | Release 1 | Security review (OWASP Top 10), dependency scan | Security | Bandit, npm audit | Developer | 2 | High | To do
T070 | S11 | Testing & Pilot | Release 1 | Unit and API tests (backend) | Testing | pytest | Developer | 4 | High | To do
T071 | S11 | Testing & Pilot | Release 1 | Frontend component and end-to-end tests | Testing | Vitest, Playwright | Developer | 4 | High | To do
T072 | S11 | Testing & Pilot | Release 1 | Permission tests: teacher/guest cannot edit or delete kids | Testing | pytest | Developer | 1 | High | To do
T073 | S11 | Testing & Pilot | Release 1 | Tests for allergy alerts, consent rules and archive/retention logic | Testing | pytest | Developer | 1 | High | To do
T074 | S11 | Testing & Pilot | Release 1 | User acceptance test with Kita staff, collect findings | Testing | Workshop | Test manager | 3 | High | To do
T075 | S11 | Testing & Pilot | Release 1 | Bug fixing and UX polish | Testing | – | Developer | 5 | High | To do
T076 | S12 | Deployment, Training & Go-live | Release 1 | Deploy production release on the Kita server; verify backups | Deployment | Docker | Developer | 2 | High | To do
T077 | S12 | Deployment, Training & Go-live | Release 1 | User manual and quick-start cards for basic users | Training | Document | Product owner | 3 | Medium | To do
T078 | S12 | Deployment, Training & Go-live | Release 1 | Staff training session and go-live | Training | – | Product owner | 1 | High | To do
T079 | S12 | Deployment, Training & Go-live | Release 1 | Support, maintenance and release process | Handover | Document | Developer | 1 | Medium | To do
T080 | S13 | Parent Communication & Documents | Release 2 | Parent role and portal login: read-only access to own child's data | Parents | FastAPI, React | Developer | 4 | Medium | To do
T081 | S13 | Parent Communication & Documents | Release 2 | Announcements and newsletters with email notification | Communication | SMTP, FastAPI | Developer | 4 | Medium | To do
T082 | S13 | Parent Communication & Documents | Release 2 | Read receipts for announcements | Communication | FastAPI | Developer | 1 | Medium | To do
T083 | S13 | Parent Communication & Documents | Release 2 | Teacher–parent messages | Communication | FastAPI, React | Developer | 4 | Low | To do
T084 | S13 | Parent Communication & Documents | Release 2 | Document templates (contracts, forms) with PDF export | Documents | WeasyPrint | Developer | 3 | Low | To do
T085 | S14 | Daily Reports, Development & Staff Ops | Release 2 | Daily report: meals, nap, mood, diapers | Daily report | React, FastAPI | Developer | 4 | Medium | To do
T086 | S14 | Daily Reports, Development & Staff Ops | Release 2 | Development observations with photos; export for parent conversations | Development | React, FastAPI | Developer | 4 | Medium | To do
T087 | S14 | Daily Reports, Development & Staff Ops | Release 2 | Staff duty roster and absences | Staff | React, FastAPI | Developer | 4 | Medium | To do
T088 | S14 | Daily Reports, Development & Staff Ops | Release 2 | Staff-to-child ratio check per group | Staff | FastAPI | Developer | 1 | Medium | To do
T089 | S14 | Daily Reports, Development & Staff Ops | Release 2 | Meal plan matched against allergies and food preferences | Meals | React, FastAPI | Developer | 3 | Medium | To do
T090 | S14 | Daily Reports, Development & Staff Ops | Release 2 | Waiting list and enrolment | Enrolment | React, FastAPI | Developer | 4 | Low | To do
T091 | S15 | AI Features | Release 2 | Define AI use cases and privacy rules (no child data to external AI without approval) | AI | Document | Product owner | 2 | High | To do
T092 | S15 | AI Features | Release 2 | Local AI runtime on server (Ollama); check hardware needs | AI | Ollama | Developer | 2 | High | To do
T093 | S15 | AI Features | Release 2 | Natural-language search over profiles, tasks, events | AI | Embeddings, pgvector | Developer | 4 | Medium | To do
T094 | S15 | AI Features | Release 2 | AI draft assistant: parent letters, announcements, weekly/development summaries (teacher reviews) | AI | Local LLM | Developer | 4 | Medium | To do
T095 | S15 | AI Features | Release 2 | Translate parent messages into the family's language (label as AI-translated) | AI | Local LLM | Developer | 3 | Medium | To do
T096 | S15 | AI Features | Release 2 | Activity suggestions from children's interests; task suggestions for the board | AI | Local LLM | Developer | 2 | Low | To do
T097 | S15 | AI Features | Release 2 | In-app help assistant for basic users | AI | LLM, RAG over manual | Developer | 3 | Medium | To do
T098 | S15 | AI Features | Release 2 | AI photo helper: tag/sort photos (no face recognition without consent) | AI | Vision model | Developer | 4 | Low | To do
T099 | S16 | Release 2 Testing & Rollout | Release 2 | Tests for new modules (parent portal, daily report, roster, AI) | Testing | pytest, Playwright | Developer | 5 | High | To do
T100 | S16 | Release 2 Testing & Rollout | Release 2 | User acceptance test with Kita staff and parent pilot group | Testing | Workshop | Test manager | 3 | High | To do
T101 | S16 | Release 2 Testing & Rollout | Release 2 | Bug fixing and polish | Testing | – | Developer | 4 | High | To do
T102 | S16 | Release 2 Testing & Rollout | Release 2 | Deploy Release 2 and train staff | Deployment | Docker | Developer | 2 | High | To do
[7 empty] | Total days | 253

## Requirements
Requirements Traceability
R01–R17 are from your list, R18–R35 are the suggested additions. Priority uses MoSCoW (Must / Should / Could).
Req ID | Requirement | Source | Delivered in stage(s) | Release | Priority | Backlog tasks | Verified in UAT?
R01 | Web interface; landing page with Login, Admin, Teacher, Guest access | Your list | S4 | Release 1 | Must | 8 | No
R02 | Teacher accounts via Gmail or GMX | Your list | S4 | Release 1 | Must | 8 | No
R03 | Admin-only page listing all logins with access rights | Your list | S4 | Release 1 | Must | 8 | No
R04 | Secure data storage on local network, accessible to all Kita users | Your list | S2, S3, S10, S12 | Release 1 | Must | 25 | No
R05 | AI-powered application | Your list | S15 | Release 2 | Should | 8 | No
R06 | Kids profile create/edit/delete, admin only | Your list | S5 | Release 1 | Must | 10 | No
R07 | Profile content: photo, name, gender, language, food preferences, interests, photos | Your list | S5 | Release 1 | Must | 10 | No
R08 | Deleted profiles archived for a defined period | Your list | S5, S10 | Release 1 | Must | 15 | No
R09 | Parents data: name, address | Your list | S5 | Release 1 | Must | 10 | No
R10 | Multiple groups (Monkey, Butterflies, Insects…) | Your list | S6 | Release 1 | Must | 5 | No
R11 | Group selection via drop-down; group-specific data window | Your list | S6 | Release 1 | Must | 5 | No
R12 | Group tasks as agile board with backlog | Your list | S6 | Release 1 | Must | 5 | No
R13 | Calendar: holidays, updates, events | Your list | S7 | Release 1 | Must | 5 | No
R14 | Clear separation of current and archived data, easy access | Your list | S5, S10 | Release 1 | Must | 15 | No
R15 | UX/HMI design for basic users | Your list | S1, S11 | Release 1 | Must | 12 | No
R16 | Report problems, change requests, ideas from the GUI | Your list | S9 | Release 1 | Must | 3 | No
R17 | Automatic crash reports to developers | Your list | S9 | Release 1 | Must | 3 | No
R18 | Allergy and medical alerts linked to food preferences | Suggested | S5, S8 | Release 1 | Must | 15 | No
R19 | Emergency contacts and authorised pick-up persons | Suggested | S5 | Release 1 | Must | 10 | No
R20 | Printable emergency / evacuation list | Suggested | S8 | Release 1 | Must | 5 | No
R21 | Daily attendance and absence notes | Suggested | S8 | Release 1 | Must | 5 | No
R22 | Consent management (photos, excursions, data); gallery respects consent | Suggested | S5 | Release 1 | Must | 10 | No
R23 | Accident and incident log | Suggested | S8 | Release 1 | Must | 5 | No
R24 | Birthday reminders in calendar | Suggested | S7 | Release 1 | Should | 5 | No
R25 | Daily report (meals, nap, mood, diapers) | Suggested | S14 | Release 2 | Should | 6 | No
R26 | Development observations and export for parent conversations | Suggested | S14 | Release 2 | Should | 6 | No
R27 | Parent communication: portal, announcements, read receipts, messages | Suggested | S13 | Release 2 | Should | 5 | No
R28 | Staff duty roster, absences and staff-to-child ratio | Suggested | S14 | Release 2 | Should | 6 | No
R29 | Meal plan matched against allergies | Suggested | S14 | Release 2 | Should | 6 | No
R30 | Waiting list and enrolment | Suggested | S14 | Release 2 | Could | 6 | No
R31 | Document templates with PDF export | Suggested | S13 | Release 2 | Could | 5 | No
R32 | Local AI: translation, drafting, suggestions, help assistant | Suggested | S15 | Release 2 | Should | 8 | No
R33 | Tablet-friendly layout / progressive web app | Suggested | S1, S2, S11 | Release 1 | Must | 19 | No
R34 | Audit log and parent data export/deletion | Suggested | S10 | Release 1 | Must | 5 | No
R35 | German/English user interface | Suggested | S1, S2 | Release 1 | Should | 13 | No

## Server Setup
Server Setup Guide (Stage S3)
Step-by-step checklist for the Kita server. Commands are examples; I will give exact commands for each step when you reach it.
Step | Action | Example / detail | Tool | Done?
1 | Decide hardware: mini PC (16 GB RAM, 512 GB NVMe) or NAS that runs Docker; plus UPS and a second drive for backups | Check what the Kita already has; for local AI later a stronger machine may be needed | – | No
2 | Install Ubuntu Server LTS; enable disk encryption (LUKS) during install | Installer option 'encrypt the LVM group' | LUKS | No
3 | Create admin user, enable SSH keys, disable password login | ssh-copy-id; PasswordAuthentication no | OpenSSH | No
4 | Reserve a fixed IP in the router and set a local name (e.g. kita.lan) | DHCP reservation; local DNS entry in router | Router | No
5 | Enable firewall: allow 22 (LAN only), 80, 443 | ufw allow from 192.168.0.0/16 to any port 22; ufw allow 80,443/tcp; ufw enable | ufw | No
6 | Do not forward any ports on the router; the app stays local only | Check router port-forwarding table is empty | Router | No
7 | Install Docker Engine and Compose plugin | Official Docker apt repository | Docker | No
8 | Deploy the stack: PostgreSQL, API, web frontend, Caddy | docker compose up -d with .env for secrets | Docker Compose | No
9 | Enable HTTPS with Caddy's internal CA; install the root certificate on Kita PCs and tablets | Export root.crt; install in OS / browser trust store | Caddy | No
10 | Mount the shared network drive for photos and documents (database stays on server disk) | /etc/fstab entry for SMB/NFS share; restrict permissions | SMB/NFS | No
11 | Nightly database backup and photo sync to second drive | cron: pg_dump ¦ gzip; rsync -a | pg_dump, rsync | No
12 | Weekly encrypted off-site backup (e.g. USB drive taken home or cloud storage in the EU/CH) | restic backup with password stored separately | restic | No
13 | Test a full restore on a spare machine or container; document the steps | Restore dump into a fresh Postgres container | pg_restore | No
14 | Turn on automatic security updates | apt install unattended-upgrades | unattended-upgrades | No
15 | Connect UPS and configure safe shutdown | NUT (Network UPS Tools) | NUT | No
16 | Add monitoring: disk space, uptime, backup success, email alert | Simple script + cron, or Uptime Kuma | Uptime Kuma | No
17 | Write the admin runbook (restart, update, restore, add/remove user) | One page, printed and kept in the Kita office | Document | No
| Steps done | 0 of 17
Rule: never put the PostgreSQL data folder on a network share – it can corrupt the database. Photos and documents may live on the share.

## Tech Stack
Proposed Technology Stack
Area | Proposal | Reason / note
Backend language | Python 3.12 | Requested language; strong AI ecosystem
Backend framework | FastAPI | Fast, typed, automatic API docs
Frontend language | TypeScript | Requested; type safety reduces bugs
Frontend framework | React + Vite (PWA) | Large ecosystem; installable on tablets
UI library | MUI or Mantine | Accessible components, large touch targets
Database | PostgreSQL | Reliable; schemas for current vs. archive; pgvector for AI search. Keep on the server's own disk, not on a network share
ORM / migrations | SQLAlchemy + Alembic | Standard Python stack
Authentication | Email + password (argon2), JWT/session cookies; optional Google OAuth | GMX has no standard third-party login; Google OAuth needs an internet-reachable redirect
Server OS | Ubuntu Server LTS with LUKS disk encryption | Stable, well documented, long support
Containers | Docker Compose | Simple install, update and rollback
Reverse proxy / HTTPS | Caddy with internal CA | Automatic local certificates
File storage | Shared network folder (photos/documents), encrypted at rest | Meets the local-network requirement
Backup | pg_dump + rsync to second drive; restic encrypted off-site | Restore tested in S3
Power / availability | UPS with NUT safe shutdown | Protects the database from power cuts
Task board | dnd-kit | Kanban drag and drop
Calendar | FullCalendar + iCal import | Holidays and events
PDF generation | WeasyPrint | Emergency list, forms, reports
Email | Local SMTP relay or provider account | Verification, notifications, feedback
AI | Local model via Ollama (preferred) – may need a stronger machine | Children's data stays on-premises
Crash reporting | Self-hosted Sentry or custom error endpoint | Automatic reports to developer
Feedback routing | Azure DevOps API / email | Creates work items
Testing | pytest, Vitest, Playwright | Backend, component and end-to-end
CI/CD | GitHub Actions or Azure DevOps Pipelines | Automated tests and builds

## Risks
Risk Register
Probability and impact: 1 = low, 3 = high (blue = input). Score = probability × impact.
ID | Risk | Probability (1-3) | Impact (1-3) | Score | Rating | Mitigation | Owner
K01 | Children's, parents' and health data; legal compliance (nDSG/DSGVO) | 3 | 3 | 9 | High | Data-protection concept in S0, consent management, minimal data, audit log, encryption | Product owner
K02 | Allergy / medical information wrong or outdated | 2 | 3 | 6 | High | Admin-only edit, review prompts, visible banners, tests in S11 | Developer
K03 | Staff find the UI too complicated | 3 | 3 | 9 | High | Prototype tests in S1, large buttons, in-app help, training | UX designer
K04 | Local server unavailable or backups not working | 2 | 3 | 6 | High | Automated backups, restore test in S3, UPS, monitoring alerts | Developer
K05 | Hardware not yet available (purchase lead time) | 2 | 2 | 4 | Medium | Decide in S0, order early, develop against Docker on your own machine meanwhile | Developer
K06 | AI sends sensitive data to external services | 2 | 3 | 6 | High | Local model, anonymise inputs, admin switch to disable AI | Developer
K07 | Local AI needs stronger hardware than the Kita server | 2 | 2 | 4 | Medium | Check in S15 first task; fall back to small models or cloud only for non-personal text | Developer
K08 | AI translation or draft contains errors | 2 | 2 | 4 | Medium | Teacher reviews before sending; label AI-generated text | Developer
K09 | Parent portal increases attack surface | 2 | 3 | 6 | High | Separate role, rate limiting, security review, delivered in Release 2 | Developer
K10 | Gmail/GMX login scope unclear (GMX has no third-party OAuth) | 3 | 2 | 6 | High | Email + password with verification; Google OAuth optional | Developer
K11 | Scope creep | 3 | 2 | 6 | High | MoSCoW, two releases, change requests via feedback form | Product owner
K12 | Single developer: long timeline and dependency on one person | 3 | 3 | 9 | High | Release 1 early with pilot, documentation, clean code, CI; adjust availability input in Stages | Developer
K13 | Photo storage grows quickly | 2 | 1 | 2 | Low | Thumbnails, size limits, storage monitoring | Developer
K14 | Accidental deletion or data loss | 1 | 3 | 3 | Medium | Admin-only delete, archive period, backups | Developer